## Sheet1
Minutes of Meeting
Project: | SATS
Subject: | Weekly Review Meeting | Meeting No:
Date: |  | Location: | Microsoft Teams/Google Meet
Scheduled Start Time: | 3:00 PM IST | Actual Start Time:
Scheduled End Time: | 4:00 PM IST | Actual End Time:
Participants:
Sl. No. | Name | Project/Process/Company
Present:-
1 | Rajiv Kumar Jain | SSTL
2 | Rajnee Vatsyayan | SSTL
3 | Sakthivel Parameswar | SSTL
4 | Ashis Malakar | UMT
5 | Abhijit Guha Thakurta | UMT
6 | Saradwata Sen | UMT
7 | Anindya Moitra | UMT
8 | Dipankar Das | UMT
9 | Rakesh Singh | UMT
10 | Ravishankar Lingaraju | SSTL
Chair Person: | Rajiv Kumar Jain
Minutes prepared by: | Ashis Malakar
Tentative date for next meeting: |  | Every Wednesday
A. Status of Issues / Action Items discussed in the previous meeting (if any)
Sl. No. | Issues / Action Items | Status | Previous Target Date for Closing | Responsibility | Plan of Action (if not closed) | Revised Target Date
B. Points Discussed
Sl. No. | Points Discussed
1 | Sprint 1 should be delivered to SSTL for functional testing as these functions were not tested by SSTL before. Rajnee will take up this testing from SSTL side.
2 | Sprint 1 functional test cases will be shared to SSTL for validation. Non-functional test cases will be prepared and shared later on with Sakhtivel, Anubhav and Rajiv.
3 | A technical spec needs to be prepared and shared with SSTL for non-functional requirements such as hardware/server environment, performance parameters, network etc.
4 | A separate plan for User Management module to be prepared with difference phases of implementation.
5 | MoM and other project realated documents should be maintained in Google Docs with project folders created in the Google Drive. This will enable all stakeholders to view and edit the documents from the shared folder.
6 | Risk register with risk identification date, mitigation plan and date etc. for the current projects risks should be shared in the weekly review.
7 | Support needed by the implementation team, if any, from any stakeholder should be asked for whenever it is required.
C. Actions Planned
Sl. No. | Initiation Date | Action Points (if any) | Responsibility | Target Date for Closing | Status | Update Date | Proposed New Date | Remarks
1 | 2023-08-31 | Release of Sprint 1 to SSTL for testing | Anindya | 2023-09-05 | Complete | 2023-09-14
2 | 2023-08-31 | Sharing of Sprint 1 functional test cases with SSTL for validation | Anindya | 2023-09-05 | Complete | 2023-09-14
3 | 2023-08-31 | Sharing technical spec for the non-functional requirements of SATS project | Ashis | 2023-09-15 | Complete | 2023-09-14
4 | 2023-08-31 | Prepare and share phase wise plan for User Management implementation | Saradwata | 2023-09-12 | Complete | 2023-09-14
5 | 2023-08-31 | Google Doc environment | Saradwata | 2023-09-01 | Complete | 2023-09-14
6 | 2023-08-31 | Include Risk Register in the new format in the weekly review PPT | Saradwata | 2023-09-06 | Complete | 2023-09-14
7 | 2023-08-31 | Include Support Needed slide in the weekly review PPT | Saradwata | 2023-09-06 | Complete | 2023-09-14
8 | 2023-09-06 | Testing results sharing daily basis | Rajnee and Harsh | 2023-09-19 | WIP | 2023-09-14
9 | 2023-09-06 | Bid team to be formed | Rajnee | 2023-09-06 | Complete | 2023-09-14
10 | 2023-09-14 | Release mobile app ipa file for iOS | Senthil and Ravi | 2023-09-14 | WIP | 2023-09-14 |  | iOS (ipa) file will be generated once issues are fixed in android version (apk).
11 | 2023-09-14 | Add Classification column in Issue register | Saradwata | 2023-09-15 | Complete | 2023-09-17
12 | 2023-09-14 | Update Risk Register with the PM integration problem | Saradwata | 2023-09-14 | Complete | 2023-09-17
13 | 2023-09-20 | Review feedback on user management mockup screens | Rajiv | 2023-09-21 |  | 2023-09-20
14 | 2023-09-20 | Test data will be provided by the development team | Anindya | 2023-09-27 | Complete | 2023-09-27