## Defects Summary
Goal | 96 | 0 | 0 | 0 | 96
2 additonal TX requirement shared
Target date for final version 14th Nov COB
16th full demo of app + TX requirement----- data set preparation
17th create demo environment for TX - Bobbin, Ashis, Ravi, Harsh
Data set requirement
1. types of tower
2. different cities
3. multiple supervisor
4. multiple technician
5. type of active loadings
6. types of different format of passive assets

## Change Management Sheet
Sl No. | CR Ref No | Date Raised | Raised By | Reference | Description | Change Category | Rationale | Remarks | Solution By | Solution Date | Agreed By | Agreed Date | Build Promised Date
1 | CR001 | 2023-11-06 | Rajiv | Mail from Rajiv | 1. Google maps depiction of all sites mapped to a given user in color coded form. No tags – White circle, Partial – Amber circle, all tagged – green circle. On mouse move of the circle other information of the site should be visible. Other standard features of google maps to be supported. 2. The mobile app should allow the phone camera to take a video grab which then can be sent the video to the backend for further processing. We can show this in the task to do list fo the supervisor. Current this basic feature would be needed. | Enhancements | These are New Features to be developed in the solution. | Version 1.4.0, date 17/11/23 | UMT | 2023-11-14 | SSTL | 2023-11-08 | 2023-11-14
2 | CR002 | 2023-10-30 | Rajnee | Issue Register (#42) | As a technician, there should be restriction for then, that when they visit to site , then only they would be able to tag, untag the asset. | Change | Change from current business logic. The use case was not part of the requirements doc. | Version 1.4.0, date 17/11/23 | UMT | 2023-11-17 | SSTL | 2023-11-08 | 2023-11-14
3 | CR003 | 2023-10-31 | Ravi | Issue Register (#56) | Asset Addition screen to be redesigned in such a way that user will be able to add parent & child assets together. | Change | Change from the approved design (mock screens) of adding assets | Major re-designing of screens and impacts on the APIs and PM | UMT | 2023-11-25 |  |  | 2023-11-24

## Screenshot
Point No 43
point 69
point 70
web view of supervisor
point 73
mobile view of techician

## Defects
Sl# | Sprint | Source | Function / Location of Issue | Issue Description | Severity | Classification | Raised Date | Raised by | UMT Comments | UMT Comment Date | Status | Date Closed | SSTL Comments | Release version (New Features and Bug Fixes)
1 | Sprint-2 | WEB | pending approval | the screen is complete black it will not even show pending approval is zero | High | FU-Functional | 2023-09-14 | Ravishankar | Not part of Sprint-1. It will be implemented in Sprint-2 to display the pending tasks from Process Maker. 21-Sep>> Please check PSR backup slides for sprint items and Requirements/HLD for the detailed functionalities at the shared drive. | 2023-09-21 | Closed | 2023-10-20 | we need to know the details of sprint 1 and sprint 2 |  | please check no detailed report is given Senthil> Sprint items were given in PSR file and details are in the HLD doc. Please check below links HLD -> https://docs.google.com/document/d/1rLHAUQ19jMSuYFSLBzZiyQwQ59P-tZIz/edit?rtpof=true PSR->https://docs.google.com/presentation/d/19we10e9Yf0bdOwSS9YkSuyxaOCDfnkqQ/edit#slide=id.p7
2 | Sprint-2 | BOTH | Overall | the application on both web and mobile will never gets logged out it remains as it | High | IM-Improvement | 2023-09-14 | Ravishankar | Logout happens once Logout option is clicked. Auto Logout is not yet implemented. It will be implemented in Sprint-2 | 2023-09-20 | Closed | 2023-10-20
3 | Sprint-1 | MOBILE | near by sites | only technician can see this, superviser not able to see | High | FU-Functional | 2023-09-14 | Ravishankar | This is working fine. Both user can see near by sites. Will add some sites to your location after that please test again. 21-Sep> Added some nearby sites. Pls check now. | 2023-09-21 | Closed | 2023-10-20 | no site as been added till now. can we know the logic which we are working on
4 | Sprint-2 | MOBILE | if technician completets task | that task complition is not refelcting supervisors account , he should gets that notification | High | IM-Improvement | 2023-09-14 | Ravishankar | In sprint-1 we are allowing to update directly to database and approval feature is not yet implemented. It will be implemented in sprint-2 because PM approval is implemented in sprint2. | 2023-09-21 | Closed | 2023-10-20
5 | Sprint-1 | MOBILE | supervisor login page | nothing is working in supervisor account | High | FU-Functional | 2023-09-14 | Ravishankar | Data issue - This is working fine. Will add some sites to your location after that please test again. 21-Sep> Added some nearby sites. Pls check now. | 2023-09-21 | Closed | 2023-10-20
6 | Sprint-1 | MOBILE | adding new asset | this is not working | High | FU-Functional | 2023-09-14 | Ravishankar | Data issue - Please let us know if you are getting any error message. 21-Sep> It is working when we are doing this. Please retest. | 2023-09-21 | Closed | 2023-10-20 | adding new asset for eg new asset found in site cannot be added only if that asset is availble in FAR or SATS directory only with that serial no its added new asset cannot be added
7 | Sprint-1 | MOBILE | qr scanner | this function is not working | High | FU-Functional | 2023-09-14 | Ravishankar | Please let us know if you are getting any error message. | 2023-09-20 | Closed | 2023-09-21
8 | Sprint-1 | MOBILE | battery bank | it is included in both active asset and passive asset as well | High | FU-Functional | 2023-09-14 | Ravishankar | Data issue - We have removed the data from active asset. Please retest | 2023-09-20 | Closed | 2023-09-21
9 | Sprint-2 | MOBILE | child asset | when we add child asset we cannot reveiw it and also this notification we cannot see in supervisior details | High | FU-Functional | 2023-09-14 | Ravishankar | In sprint-1 we are allowing to update directly to database and approval feature is not yet implemented. It will be implemented in sprint-2 because PM approval is implemented in sprint2. | 2023-09-20 | Closed | 2023-10-20
10 | Sprint-2 | MOBILE | child asset details | incomplete information of child asset and we cannot see that when it is added and date, time and image. | High | FU-Functional | 2023-09-14 | Ravishankar | Data issue - Those could be dynamic attributes and not configured yet. Configuration management will be in sprint-2. | 2023-09-21 | Closed | 2023-10-20 | marked as irrlevant but when will be configured kindly provide us the details
11 | Sprint-2 | WEB | Operator site view | No image shown on desktop version | High | UI-Screen Cosmetics | 2023-09-14 | Ravishankar | Image view is not yet implemented in Web Protal. It will be implemented in Sprint2. | 2023-09-21 | Closed | 2023-10-20
12 | Sprint-1 | WEB | Asset History | No asset history for asset number: AT0011345AB | Low | MI-Minor | 2023-09-14 | Ravishankar | Data issue - History data not present for this assets. You can check serial no. DK12345239 | 2023-09-21 | Closed | 2023-10-20
13 | Sprint-1 | BOTH | No version | No IOS version available | Low | FU-Functional | 2023-09-14 | Harshajit Kalita | Communication started between Senthil & Ravishankar. Apple developer account is required for this. 27-Sep> Will generate IPA once android issues get resolved | 2023-09-27 | Closed | 2023-10-20 | As per UMT ios will be developed once the final version of Android is ready.
14 | Sprint-1 | WEB | Technician to Site Tagging Status | Some status dont match with color code eg: Showing red color code in Active status Asset (http://115.113.197.12:88/public/index.php/Technician_site_Worklist_view) | Medium | MI-Minor | 2023-09-14 | Harshajit Kalita | If there is no Asset Tag No then the color code for the asset will be red. No relation between asset status & tag colour. 21-Sep> No relation between tag color and asset status. If it is not tagged then the color will be red, if tagged then color will be green. | 2023-09-21 | Closed | 2023-10-20 | Misunderstood the feature, clarified by UMT
15 | Sprint-1 | BOTH | Technician to Site Tagging Status | Naming convention is similar for type of asset (Active/ Passive) and status of asset (Active/inactive) | Low | IM-Improvement | 2023-09-14 | Harshajit Kalita | Asset Type will be either Active or Passive. Status of asset could be Active,Defective,Inactive,Missing,Redundant,Scrap 30-Oct> The Status value 'Active' will be rephrased as 'In Use'. | 2023-10-19 | Closed | 2023-10-19 | It was a suggestion and not necessary, but its confusing which was also raised by Crest in the Demo, Kindly have a look.
16 | Sprint-1 | WEB | Search Bar | Pressing Enter does does function, for search any field pressing enter does not work | Medium | MI-Minor | 2023-09-14 | Harshajit Kalita | The search is working on keypress, no need to press enter. 29-Sep> There is no enter button to search at Web App. Search works when user types text at the search box. | 2023-09-29 | Closed | 2023-10-20 | kindly provide us details why is it irrelevant, why the enter button will not work
17 | Sprint-1 | MOBILE | password | only once we can change the password after that we are unable to change it | Low | FU-Functional | 2023-09-21 | Ravishankar | 28-Sep> Change password working fine, please re-test. 31-Oct> Access control issue which is fixed and working fine. | 2023-10-31 | Closed | 2023-10-20 | facing the same issure still in new apk which is a new release in the sprint 3 |  | still not used new apk once its working fine will close it
18 | Sprint-1 | MOBILE | Task list | task list is not showing in the app | Low | FU-Functional | 2023-09-21 | Ravishankar | Please enter to this site "ST-WB-265", task list is there for this site | 2023-09-21 | Closed | 2023-10-20 |  |  | Work flow issues
19 | Sprint-1 | MOBILE | asset audit button | this is not working | Low | FU-Functional | 2023-09-21 | Ravishankar | Login as Supervisor, enter into a site which having assests, then select audit option from hamburger menu | 2023-09-21 | Closed | 2023-10-20 |  |  | Work flow issues
20 | Sprint-1 | MOBILE | Validate Search button | even after searching valid site id its saying data not found | Low | FU-Functional | 2023-09-21 | Ravishankar | Please provide the site ID which you are trying to search | 2023-09-21 | Closed | 2023-10-20
21 | Sprint-1 | MOBILE | Task list | task list is not showing in the app | Low | FU-Functional | 2023-09-22 | Ravishankar | This site "ST/HP/001", the data is not loading, working on this. | 2023-09-22 | Closed | 2023-10-20
22 | Sprint-1 | BOTH | case senstive | all functions works only on capslock only no small will work | Medium | FU-Functional | 2023-09-28 | Ravishankar | Please mention which screen and where? It is working fine with both lower and upper case. Please check again. | 2023-09-29 | Closed | 2023-10-20
23 | Sprint-2 | MOBILE | adding new asset | adding new asset is not possible if the asset not in FAR | High | FU-Functional | 2023-09-28 | Ravishankar | It is a change in existing functionality. Will be done in Sprint2. Will be available in upcoming release. 31-Oct> Implemented. | 2023-10-31 | Closed | 2023-11-02 | still improvement is required
24 | Sprint-2 | MOBILE | Adding child asset | adding new child asset is not possible if the asset not in FAR | High | FU-Functional | 2023-09-28 | Ravishankar | It is a change in existing functionality. Will be done in Sprint2. Will be available in upcoming release. 31-Oct> Implemented. | 2023-10-31 | Closed | 2023-11-02 | still it is not yet implimented
25 | Sprint-1 | BOTH | Task list and asset audit | presently tasklist is not showing in the app plus web, and it should be categorized according priority, and as well as site wise and date wise as well | High | FU-Functional | 2023-09-28 | Ravishankar | Task list (SRN, STN) is present at the Mobile App. Task list (approval request) for Supervisor will be present in screen at the WebApp and will be present in Sprint2. | 2023-09-29 | Closed | 2023-10-20
26 | Sprint-1 | MOBILE | Edit and modification | if we editing any asset only active or inactive status can be changed other things to be worked on it which will be mandatory points | High | FU-Functional | 2023-09-28 | Ravishankar | Status and Other fields are also editable. Working fine. 31-Oct> Attributes edit/modification is working fine. | 2023-10-31 | Closed | 2023-11-02 | edit and modification we need improvement in the attribute details
27 | Sprint-1 | MOBILE | asset audit button | once we scan during if we verify details, in asset details matching button only yes will work no button is not working | High | FU-Functional | 2023-09-28 | Ravishankar | This issue is fixed and will be available in upcoming release. | 2023-09-29 | Closed | 2023-10-20
28 | Sprint-1 | MOBILE | supervisor login page | if supervisor user clicks on any near by sites he himself get a notification by this will notified to supervisor but this is not working in technician user | High | FU-Functional | 2023-09-28 | Ravishankar | This is working fine for us, please note that that message appears when user clicks on the sites which are not in 'My Sites'. | 2023-09-29 | Closed | 2023-10-21
29 | Sprint-2 | BOTH | auto logout | auto logout after 30 min is implimented as per discussion it was implimentd in sprint 2 | Low | NF-Non-functional | 2023-10-11 | Ravishankar | Web Portal auto logout is set to 10 minutes. 11-Oct> Mobile APP side implementation work in progress 27-Oct> Resolved and released in 27Oct apk. 1-Nov> Resolved. 2-Nov> Not Resolved. Working on it. 3-Nov> Resolved. System will auto logout after 10 minutes of idle time. | 2023-11-03 | Closed |  | facing same issue still kindly look into it
30 | Sprint-2 | WEB | adding new asset type | adding new asset type is possible but cannot save it | Medium | FU-Functional | 2023-10-11 | Ravishankar | This one is resolved. Kindly re-check. | 2023-10-11 | Closed | 2023-10-21 | this is not resolved kindly check
31 | Sprint-2 | WEB | configaration management | need have details about date and the creator of the dataset(site) | Low | IM-Improvement | 2023-10-11 | Ravishankar | This is done. Configuration Managemenr>Site>Site> 'Creation Date' and 'Created By' displayed. | 2023-11-02 | Resolved |  | need a walk through about this |  | need a walk through once its done i will close it.
32 | Sprint-2 | WEB | adding new asset type | adding a new asset is not possible and manufacture date is which we are not entering its not accepting | Medium | FU-Functional | 2023-10-13 | Ravishankar | Issue is not clear, please retest with latest apk. | 2023-10-14 | Closed | 2023-10-21
33 | Sprint-2 | WEB | site asset view | date filter is required for approvals on the priority basis | Low | IM-Improvement | 2023-10-13 | Ravishankar | Scope of improvement, working on it. 07-Nov> Site Creation Date implemented with filter. | 2023-11-07 | Resolved |  | need still improvement | 1.2.0 date 7/11/23 | need a walk through regarding this.
34 | Sprint-2 | WEB | proceess maker | accept and reject button is not working | Medium | FU-Functional | 2023-10-13 | Ravishankar | This is resolved. Please retest. Accept & Reject is working now. | 2023-10-14 | Closed | 2023-10-21 | still waiting for KT about Process maker
35 | Sprint-2 | BOTH | in site list assets are more in web but when we are checking in mobile it shows less | in site list assets are more in web but when we are checking in mobile it shows less Eg:site ID KA-088 bangalore | Medium | DI-Data Issue | 2023-10-13 | Ravishankar | Please recheck. | 2023-10-14 | Closed | 2023-10-21
36 | Sprint-2 | WEB | proceess maker | when ticket is raised no mails are received for registered users | Medium | FU-Functional | 2023-10-13 | Ravishankar | Please recheck. | 2023-10-14 | Closed | 2023-11-02
37 | Sprint-3 | MOBILE | Add Asset | we are not able to add asset even after giving the correct input | High | FU-Functional | 2023-10-26 | Ravishankar | Add Asset access right missing, hence access right given to technician to add new asset. | 2023-10-26 | Closed | 2023-11-02
38 | Sprint-3 | MOBILE | Asset Tagging | once the technician tags an asset, thatt notification is not reflecting in webportal and also not receiving any mail regarding that | High | FU-Functional | 2023-10-26 | Ravishankar | This issue is fixed and released in sats_27oct23.apk | 2023-10-27 | Closed | 2023-11-02 | again recived new apk on 31st oct the apk is gets crashed instantly or in the condtion where it is not responsive kindly look on to it
39 | Sprint-3 | WEB | process maker | we can not reject any approval of asset in process maker | High | FU-Functional | 2023-10-26 | Ravishankar | This issue is fixed and released in sats_27oct23.apk | 2023-10-27 | Closed | 2023-11-02
40 | Sprint-3 | MOBILE | auto logout | application is getting logged out many times even while using the application | High | FU-Functional | 2023-10-26 | Ravishankar | This issue is fixed and released in sats_27oct23.apk | 2023-10-27 | Closed |  | received new apk on 31st oct we are still facing certain crash of apk kinldy provide us proper apk we can do the complete testing on it
41 | Sprint-3 | MOBILE | perfomance issue | The apk is lagging so much and consuming a bettery so much | High | FU-Functional | 2023-10-26 | Ravishankar | Working on improvement areas. 14-Nov> Improved performance and screen freezing issue. | 2023-11-14 | Closed |  |  | 1.3.0 date 14/11/23
42 | Sprint-3 | MOBILE | Functional | As a technician, there should be restriction for then, that when they visit to site , then only they would be able to view the asset and be able to tag, untag the asset | Medium | IM-Improvement | 2023-10-30 | Rajnee | Need further discussion on this enhancement. 2-Nov> On hold now as per discussion. 8-Nov> New validation to be implemented. 16-Nov> Resolved | 2023-11-17 | Resolved |  |  | 1.4.0 date 17/11/23
43 | Sprint-3 | WEB | Funtional | User Management board should be removed from the dashboardm if we login to user mgmt, or should be highlighted to differnt color,as when we click it , it goes to some failure msg. | Low | IM-Improvement | 2023-10-30 | Rajnee | Resolved | 2023-10-30 | Closed | 2023-11-08
44 | Sprint-3 | MOBILE | My task | while clicking on My task it is not redirecting to my as mentioned in test cases | Low | FU-Functional | 2023-10-30 | Ravishankar | My Task is now changed to Task List and working fine. | 2023-10-30 | Closed | 2023-11-08
45 | Sprint-3 | MOBILE | change password | technician and supervisor can not change password the message displays this user dont have an access to change the password | Medium | FU-Functional | 2023-10-30 | Ravishankar | Access rights granted to the respective roles. | 2023-10-30 | Closed | 2023-11-08
46 | Sprint-3 | MOBILE | both technician and supervisor can search the site | this access should be restricted to supervisor | Medium | IM-Improvement | 2023-10-30 | Ravishankar | This can be restricted with respective Access rights which is configurable. | 2023-10-30 | Resolved |  | need a walk through |  | need a demonstration how it can be configured
47 | Sprint-3 | MOBILE | Validate the Email to the supervisor | if technician opens any site pop will appear saying unassigned site but this notfication is not sent to supervisor. | Medium | FU-Functional | 2023-10-30 | Ravishankar | Resolved | 2023-10-30 | Closed | 2023-11-08 | still no notification is to supervisor on this
48 | Sprint-3 | WEB | New User not recieving mail | When a new user is added in user managment, doesnt recieve any mail notification | High | FU-Functional | 2023-10-30 | Rajnee | Resolved | 2023-10-31 | Closed | 2023-11-08 | not resolved kindly recheck it
49 | Sprint-3 | MOBILE | edit of asset | in the edit option we need improvise the attribute details , now it shows only asset name, status and make we need to add some more details in it | Medium | IM-Improvement | 2023-10-30 | Ravishankar | Please configure more asset attribute and then edit. | 2023-10-31 | Closed | 2023-11-08 | need an explaination
50 | Sprint-3 | MOBILE | adding child asset | when we are adding child asset we dont have option of tagging it and taking a picture of it | High | FU-Functional | 2023-10-30 | Ravishankar | 07-Nov> Resolved. | 2023-10-30 | Closed | 2023-11-08 |  | 1.2.0 date 7/11/23
51 | Sprint-3 | MOBILE | adding child asset | adding child asset is not notified to supervisor | Medium | FU-Functional | 2023-10-30 | Ravishankar | This is working fine. | 2023-10-31 | Closed | 2023-11-08
52 | Sprint-3 | MOBILE | auto logout | even still while using the application gets auto logout | Low | FU-Functional | 2023-10-30 | Ravishankar | Duplicate (#29) | 2023-10-31 | Closed | 2023-10-31
53 | Sprint-3 | MOBILE | multiple user | in same account simultaneously multiple users can login and can use | Low | FU-Functional | 2023-10-30 | Ravishankar | As per Ravi, multiple active session should not be allowed for same user. 07-Nov> As discussed with Mr. Rajiv, this will be kept as it is during the testing phase. Multi login will be stopped during project implemntation. | 2023-10-31 | Closed |  | during testing we need have certain test cases for this as well | 1.2.0 date 7/11/23
54 | Sprint-3 | MOBILE | asset addition | even if we are adding invalid details during asset addition its gets added | Low | FU-Functional | 2023-10-31 | Ravishankar | It is a freeflow field. | 2023-10-31 | Closed | 2023-11-02 | there must be certain fixed attributes but it accepts everything
55 | Sprint-3 | MOBILE | asset addition | during asset addition we dont have option to tag and take a picture of new asset | High | FU-Functional | 2023-10-31 | Ravishankar | Tag button is present at the Add New Asset screen. | 2023-10-31 | Closed | 2023-11-08 | not resolved kidnly recheck it | 1.2.0 date 7/11/23
56 | Sprint-3 | MOBILE | asset addition | while adding new asset if that asset as a child asset we dont have an option to add any child asset for that new asset | Medium | IM-Improvement | 2023-10-31 | Ravishankar | User will add parent asset first and then go for adding childs. 7-Nov> This is a modification in the existing design. Asset Addition screen will be redesigned in such a way that user will be able to add parent & child assets together. 17-Nov> Planned to release on 24-Nov | 2023-11-25 | Closed |  | so need to do the process twice we can not do at a time | 1.5.0 date 25/11/23
57 | Sprint-3 | MOBILE | QR code | scanned same QR code for many assets it accepted it and it did not show any error on. QR code should be always unique for every single asset | High | FU-Functional | 2023-10-31 | Ravishankar | 07-Nov> Resolved. | 2023-11-01 | Closed | 2023-11-08 | not working fine we tag same QR code for many assets | 1.2.0 date 7/11/23
58 | Sprint-3 | MOBILE | STN process | we have to match the asset details which are matching ,but if those details are not matching we dont any option for miss match | High | FU-Functional | 2023-10-31 | Ravishankar | STN Details would be editable and in case of mismatch user will modify and submit STN. 07-Nov> Resolved. | 2023-11-01 | Closed | 2023-11-08 | no option availble in application kindly recheck | 1.2.0 date 7/11/23 | now we are able to get that option in in new relase but no nofitication is received regarding this to any users.
59 | Sprint-3 | BOTH | SRN | while rejecting srn no notification sent to supervisor and it still remains in task list unless we accept it | High | FU-Functional | 2023-10-31 | Ravishankar | SRN will not appear in task list after rejection. Also technician will get email about the SRN rejection by supervisor. 07-Nov> Resolved. | 2023-11-01 | Closed |  | we have not got any mail | 1.2.0 date 7/11/23 | not receiving any mail
60 | Sprint-3 | MOBILE | STN process | technician can not see any details about the asset in STN process he as site address and remarks need more information to identify on it | Low | IM-Improvement | 2023-10-31 | Ravishankar | User can see the details after opening the STN. | 2023-11-01 | Closed | 2023-11-02
61 | Sprint-3 | MOBILE | STN and SRN | while asset tagging technician can not click on ok button to submit its not working and in both STN and SRN submit button is not working | high | FU-Functional | 2023-10-31 | Ravishankar | Unable to replicate this issue. Working fine for us. Please recheck. | 2023-11-01 | Closed | 2023-11-08 | when unable to replicate the issue how is it resolved??
62 | Sprint-3 | BOTH | login | during login if we are entering the first letter in caps we will be not able to login it throws an error | Medium | FU-Functional | 2023-10-31 | Ravishankar | User id is made case insensitive. Please re-check. | 2023-11-03 | Closed | 2023-11-08 | not resolved kindly close only if it is closed | 1.2.0 date 7/11/23
63 | Sprint-3 | MOBILE | asset audit | once asset audit is done and colour code turns green, and if reclick on asset audit again it shows red in colour we can redo the asset audit. unless ticket raised by the user is cleared how can we redo the audit for the same asset | Medium | IM-Improvement | 2023-10-31 | Ravishankar | Need further discussion on this enhancement. 1-Nov> As per discussion in review meeting, no change is required in audit process right now. Any changes in the existing audit process can be discussed in future. | 2023-11-01 | Closed | 2023-11-02
64 | Sprint-3 | WEB | user management | the check box which is provided when user is created, only supervisor check box is availble but a check box for all the roles should be there | medium | IM-Improvement | 2023-10-31 | Rajnee | Check box is not required for other roles than supervisor. This check box is given so that system can identify the supervisor user during Technician-Supervisor mapping.. | 2023-11-01 | Closed
65 | Sprint-3 | WEB |  | who creates admin id | Low | FU-Functional | 2023-10-31 | Rajnee | This is Query. This is the default user of the system and will be used to create first user in the system. | 2023-11-01 | Closed
66 | Sprint-3 | WEB | login details | in the web portal the user dont have any option to reset the password | Medium | IM-Improvement | 2023-10-31 | Ravishankar | User will login into user mangement and do change password. Use forgot password option from user managment | 2023-11-01 | Closed |  | there must be reset option for password in webportal for every users
67 | Sprint-3 | MOBILE | asset addition | while adding new asset if we are adding the availble asset with same serial it adds the asset and say the asset is not found | High | FU-Functional | 2023-11-02 | Ravishankar | This issue is resolved. | 2023-11-03 | Closed |  | how can we close the issue still we have recived the apk and not tested | 1.2.0 date 7/11/23
68 | Sprint-3 | WEB | user Management | whenever new user is created, welcome mail recieved by the user is incomplete | Medium | MI-Minor | 2023-11-03 | Rajnee | 07-Nov> After user creation, admin user will receive mail like below: Dear Admin, A user is created for your review and Activation. User Email : <> Thanks, Asset Tagging System | 2023-11-03 | Closed | 2023-11-08 | Welcome mail, along with what to donwload or where to downlaod even credentials are needed | 1.2.0 date 7/11/23
69 | Sprint-3 | MOBILE | Add Asset | while addition an asset, for diameter are able to enter alphanumeric value | Low | MI-Minor | 2023-11-03 | Rajnee | Changed the Data Type of this attribute as Numeric. 07-Nov> Resolved. | 2023-11-06 | Closed | 2023-11-08 |  | 1.2.0 date 7/11/23
70 | Sprint-3 | WEB | Add Site | while adding a new site from the id of Harshajit , save button is not working | High | FU-Functional | 2023-11-07 | Rajnee | Just Created site 'HK-T001' using user Harshajit, no issue found, requesting to please check again. | 2023-11-07 | Closed | 2023-11-08 | shared recording to ashis
71 | Sprint-3 | WEB | user Management | while a new technician is added and phased is chnged from pending to active, no mail has been floated to admin as well as to the technician | High | FU-Functional | 2023-11-07 | Rajnee | After user activation by admin, the user will receive mail like below: Dear User, Login creadentials have been created for you to access Asset Tracking System (ATS) with following: Email : <> Password : <> Use below link to access Web Portal: http://115.113.197.12/usermanagement/public/login Also download and install the ATS Mobile App from Play store. Thanks, ATS Administrator | 2023-11-10 | Closed | 2023-11-08 |  | 1.2.0 date 7/11/23
72 | Sprint-3 | WEB | server error | while using supervisor id, contionous server error is coming | High | FU-Functional | 2023-11-07 | Rajnee | 07-Nov> Resolved. | 2023-11-07 | Resolved |  |  | 1.2.0 date 7/11/23
73 | Sprint-3 | WEB | site to technician mapping | supervisor Harshajit created 2 sites( BL-001 & BL-010), alloted 1 site each to 2 technician( Rajnee & Swaleha) through batch process, but it has not be mapped to technician | High | FU-Functional | 2023-11-08 | Rajnee | 14-Nov> This has been resolved. Please check. 15-Nov> Please re-check. | 2023-11-15 | Resolved |  | Supervisor created 3 sites BL-020,BL-021, BL-022. Allocated it to technician( swaleha, rajnee, jaya). while allocation jaya and swaleha were mappped to the respective site. but Rajnee was not alloted with the site( when super visor was check in web portal. but when rajnee checked in her mobile app , she was able to see that site. 15/11 - still BL-020 is not mapped to the technician Rajnee | 1.3.0 date 14/11/23
74 | Sprint-3 | WEB | batch process( query) | what does the batch process file ( action flag ) potraits | Medium | FU-Functional | 2023-11-08 | Rajnee | Allocate- Assigning site to the technician Deallocate- Removing technician from an assigned site | 2023-11-13 | Closed
75 | Sprint-3 | WEB | batch process | a message should flash post the batch process is over | Medium | IM-Improvement | 2023-11-08 | Rajnee | Message has been introduced. Please check. | 2023-11-13 | Closed
76 | Sprint-3 | MOBILE | login credential | if we click on forgot password in login page that feautre is not working | High | FU-Functional | 2023-11-09 | Ravishankar | 14-Nov> Resolved | 2023-11-14 | Closed |  |  | 1.3.0 date 14/11/23
77 | Sprint-3 | MOBILE | technician user | technician can open any site by searching , those site are not assigned him and not notification is sent to supervisor i.e.Warning messages should shown i.e : "You tried to access the details of a site not assigned to you. Your supervisor will be notified" | High | FU-Functional | 2023-11-09 | Ravishankar | This is resolved. Please check. | 2023-11-09 | Closed
78 | Sprint-3 | MOBILE | asset addition | cannot add the new tag i.e QR code for every new code it say it already exists | High | FU-Functional | 2023-11-09 | Ravishankar | 14-Nov>Resolved | 2023-11-14 | Closed |  |  | 1.3.0 date 14/11/23
79 | Sprint-3 | MOBILE | asset addition | unable to add child asset . active asset cannot be added | High | FU-Functional | 2023-11-09 | Ravishankar | 14-Nov>Please test again with new apk dated | 2023-11-14 | Closed |  |  | 1.3.0 date 14/11/23
80 | Sprint-3 | MOBILE | asset addition | when added passive child its not showing in mobile app and also not got notification for approval as well | High | FU-Functional | 2023-11-09 | Ravishankar | 14-Nov>Resolved | 2023-11-14 | Closed |  |  | 1.3.0 date 14/11/23
81 | Sprint-3 | MOBILE | add asset | while adding new asset during subimition it says the asset is already available in site. unable add any new asset | High | FU-Functional | 2023-11-09 | Ravishankar | 14-Nov>Resolved | 2023-11-14 | Closed |  |  | 1.3.0 date 14/11/23
82 | Sprint-3 | MOBILE | addition of child asset while adding new asset | cannot add a child asset simultaneously during addition of new asset | High | IM-Improvement | 2023-11-09 | Ravishankar | Same as #56 which is already open. Please close this one. | 2023-11-10 | Closed
83 | Sprint-3 | MOBILE | SRN | in SRN if we are clicking on missmatch option. we are not reciving any notification | High | FU-Functional | 2023-11-09 | Ravishankar | 14-Nov>Resolved | 2023-11-14 | Resolved |  |  | 1.3.0 date 14/11/23 | need certain details regarding this.
84 | Sprint-3 | MOBILE | site audit | during site audit if we click on options like asset missing or tag missing colour changes to green. if we go back and revisit that page it shows aging in red colour | High | FU-Functional | 2023-11-09 | Ravishankar | As per discussion in review meeting on 01-Nov, no change is required in audit process right now. Any changes in the existing audit process can be discussed in future. Refer #63. | 2023-11-10 | Closed
85 | Sprint-3 | BOTH | auto logout | the mobile application is not loggig out it remains open even if we not using the application | High | FU-Functional | 2023-11-09 | Ravishankar | This working fine. Please check. For Mobile App- logout time is 10min For Web- logout time is 20min | 2023-11-09 | Closed
86 | Sprint-3 | BOTH | templetes | required unique mail templete for all notification mail | High | IM-Improvement | 2023-11-09 | Ravishankar | Please provide the mail templates. | 2023-11-09 | Closed
87 | Sprint-3 | WEB | technician mapping | rajnee as technician is coming twice in screen, | High | FU-Functional | 2023-11-15 | Rajnee | Please re-check and let me know where you see this. | 2023-11-15 | Closed
88 | Sprint-3 | MOBILE | UI of mobile app | technician should able to see only his sites, this as come on top and in the bottom we required near by sites with dropdown menu | High | IM-Improvement | 2023-11-09 | Ravishankar | 15-Nov> This is a change and need confirmation from Rajiv sir. 16-Nov> As per todays discussion, consolidated list of UI changes will be shared by SSTL. | 2023-11-16 | Open
89 | Sprint-3 | WEB | technician supervisor mapping | supervisor should be restricted to add any technician in their squad | Medium | IM-Improvement | 2023-11-15 | Rajnee | Role based access control is present for "Technician Supervisor Mapping". The access right is revoked from Supervisor role. Please check. | 2023-11-15 | Resolved |  |  |  | need a walkthrough about this
90 | Sprint-3 | WEB | technician record view | Supervisor should be able to see only those technicians who are reporting to him | Medium | FU-Functional | 2023-11-15 | Rajnee | Yes, supervisor can see only those technicians who are reporting to him at the "Technician to Site Tagging Status" screen. | 2023-11-15 | Resolved
91 | Sprint-3 | WEB | adding technician to supervisor | admin ( operation ) should be having the rights of mapping technician to supervisor | Medium | FU-Functional | 2023-11-15 | Rajnee | The access right for "Technician to Site Tagging Status" is given to Administrator role. | 2023-11-15 | Resolved
92 | Sprint-3 | MOBILE | Add new Asset | When trying to add new asset over the site, test 3 field is being mandatory , it is not allowing to write anything into it | High | FU-Functional | 2023-11-15 | Rajnee | 15-Nov> Resolved. | 2023-11-17 | Resolved |  |  | 1.4.0 date 17/11/23
93 | Sprint-3 | MOBILE | Additonal of Child Asset | When trying to add new child asset over the site, test 3 field is being mandatory , it is not allowing to write anything into it | High | FU-Functional | 2023-11-15 | Rajnee | 15-Nov> Resolved | 2023-11-17 | Resolved |  |  | 1.4.0 date 17/11/23
94 | Sprint-3 | WEB | pending approval | unable to accept or reject in it | High | FU-Functional | 2023-11-20 | Ravishankar | Tested and found working fine. Please let us know 'Case No' from Pending Approval screen so that we can check further. | 2023-11-22 | Closed
95 | Sprint-3 | WEB | pending approval | we get server very offently | High | FU-Functional | 2023-11-20 | Ravishankar | Resolved, please check. | 2023-11-22 | Resolved |  | already shared the screen shot in group, which says server error kindly refer the screen shot ,, facing the same issue kindly look into it |  | already shared the screen shot in group, which says server error kindly refer the screen shot ,, facing the same issue kindly look into it
96 | Sprint-3 | WEB | web portal | unable to login to we portal shows server error | High | FU-Functional | 2023-12-11 | Ravishankar | Resolved and informed Ravi. Please check and close. UMT firewall was blocking port. | 2023-12-11 | Closed
97 | Sprint-3 | BOTH | asset relations | minimum 3 level of hierarchy is what required, parent, chlid, grandchlid, required | High | FU-Functional | 2023-12-20 | Ravishankar | "Only 2-level Asset hierarchy will be supported and hence a child asset won’t have further child assets." Please refer slide#12 of PSR (Points confirmed in review meeting): https://docs.google.com/presentation/d/19flpcw-1MpjwRKR-K8oKEQk0G1kHoHC_/edit?usp=drive_link&ouid=101003619261587071789&rtpof=true&sd=true However, we can support multilevel asset hierarchy with minimum customization. 5-Jan-24> Released. | 2023-12-21 | Resolved |  |  | 1.6.0 date 05/01/24
98 | Sprint-3 | WEB | asset serach on list and map | kindly refer section 6.3.1 intial document | High | FU-Functional | 2023-12-20 | Ravishankar | Mockup 'Asset View' screens were designed initially but those were discarded during mockup screen finalization and added new screens (Technician to Site Tagging Status, Operator Site View) that are not present in the initial requirement document. Please refer the final mockup screens document shared at the drive. Also refer slide#12 of PSR (second last point). 03-Jan-24> Web portal view for Asset listing/map/filter/search could be developed as per the customer’s requirement in future so that it would be useful for respective customers. | 2023-12-21 | Resolved
99 | Sprint-3 | MOBILE | Asset search on mobile applicaton | kindly refer section 6.3.2 intial document | High | FU-Functional | 2023-12-20 | Ravishankar | Mockup 'Asset View' screens were designed initially but those were discarded during mockup screen finalization and added new screens (Technician to Site Tagging Status, Operator Site View) that are not present in the initial requirement document. Please refer the final mockup screens document shared at the drive. Also refer slide#12 of PSR (second last point). 03-Jan-24> Web portal view for Asset listing/map/filter/search could be developed as per the customer’s requirement in future so that it would be useful for respective customers. | 2023-12-21 | Resolved
100 | Sprint-3 | WEB | Asset Tag history | kindly refer section 6.3.5 intial document | High | FU-Functional | 2023-12-20 | Ravishankar | "History" screen was re-designed during mockup screen finalization and accordingly development has been done. Please refer the final mockup screens document shared at the drive. However, we are working further to enhance the history view to display tag information. 5-Jan-24> Released. | 2023-12-21 | Resolved |  |  | 1.6.0 date 05/01/24
101 | Sprint-3 | WEB | Asset view | kindly refer section 6.4.4 and 6.4.5 intial document | High | FU-Functional | 2023-12-20 | Ravishankar | Location-wise asset view is same as Site-wise asset view which is already present. The word 'Location' is replaced with 'Site' during mockup screen finalization. | 2023-12-21 | Resolved
102 | Sprint-3 | WEB | Interface | we have only file based interface and api based interface is not availble | High | FU-Functional | 2023-12-20 | Ravishankar | File based integration is in scope in this phase. API integrations may be scoped during implementation of customer project on case to case basis. | 2023-12-21 | Resolved
103 | Sprint-3 | WEB | batch process | kindly refer section 7 intial document | High | FU-Functional | 2023-12-20 | Ravishankar | The batch porcess scenarios have been implemented with respect to Process Maker integration. Please refer to the first point of PSR slide#12 instead of initial document. "Batch Process approval feature needs to be done by integrating with Process Maker. All these approval activities would be carried out individually (not in bulk) one at a time using Process Maker." Also refer PSR for Sprint2- Batch process items in slide#10. | 2023-12-21 | Resolved
104 | Sprint-3 | WEB | Reports | pending | High | FU-Functional | 2023-12-20 | Ravishankar | Report is not in scope of current phase. Reports will be developed later as per the customer requirements. | 2023-12-21 | Resolved
105 | Sprint-3 | MOBILE | IOS application | pending | High | FU-Functional | 2023-12-20 | Ravishankar | 21-Dec> Action pending from SSTL side. 02-Jan-24> Apple Developer account details received. | 2024-01-02 | In-Progress
1 |  | MOBILE | Configuratiom Management | When an new asset is added by supervisor over a web app, when status of that asset marked as invalid, still the technicain is able to add creds ofthat added asset , while saving it throws the msg " select operator type" | High | FU-Functional | 2024-04-22 | rajnee
Resolution Time (UMT)
|  |  | High | 24 hours
|  |  | Medium | 36 hours
|  |  | Low | 48 hours
Retesting time (SSTL)
|  |  | High | 24 hours
|  |  | Medium | 36 hours
|  |  | Low | 48 hours

## Actions from Meeting
Sl No. | Topic | Date Raised | Details | UMT Responsibility | SSTL Responsibility | Business Owner | Date Promised | Date Actual | Revised Date | SSTL Comments
1 | iOS app | 2023-11-01 | Apple Developer account with credentials required and Plan needs to be prepared | Ashis | Bobbin | Ravi / Harsh | 2023-11-10 |  | 2023-12-15 | Not Approved by Apple yet. Will be done by 6th Dec. Post this APK dev would start and testing and approval to Apple before this could be tested. Expect to be done 7 days post above. 13th dec
2 | SSL | 2023-11-01 | SSTL domain or subdomain with SSL |  | Bobbin/Ramesh | Ravi / Harsh | 2023-11-17 |  | 2023-11-16 | Not Approved yet by chakra. Target 1st Dec
3 | Release Note | 2023-11-01 | Release Note for 7-Nov Release | Ashis |  | Ravi / Harsh | 2023-11-09 | 2023-11-09 |  | Completed
4 | Demo | 2023-11-01 | Demo data set preparation | Ashis | Ravi | Ravi / Harsh | 2023-11-16 | 2023-11-16 |  | Completed
5 | Demo for Ascend | 2023-12-05 | Confirmation on any demo related requirement need from UMT 1. Gap analysis by Ravi to be sharred by 16th Dec |  | Ravi |  | 2023-12-16 |  |  | Ravi to provide details on instance. data preparedness for demo
6 | All Defects | 2023-12-05 | All defects to be closed by Ravi and Rajnee | Ashis | Ravi / Rajnee |  | 2023-12-06
7 | CR approval | 2023-12-05 | UMT to show that the stated requirement is mentioned such that CR003 is a change. | Ashis | Rajiv |  | 2023-12-05 | 2023-12-05
Hours
|  |  | Configuring App Signing: -Creating an App ID -Creating Provisioning Profiles | 2
|  |  | Testing App: -Connecting an iOS Device -Setting up the device for development -Testing App: Varied, depending on the testing scope. | 6
|  |  | Preparing for App Store Submission: -Creating App Store Connect Record -Preparing App Assets | 4
|  |  | Archiving and Distributing App: -Building Archive -Submitting to App Store | 3
|  |  | App Review and Distribution: -Submitting for Review -Waiting for Approval: Several days to a week or more, depending on the review queue. -Releasing App | 1