## Sheet1
Sl# | Sprint | Source | Function / Location of Issue | Issue Description | Severity | Classification | Raised Date | Raised by | UMT Comments | UMT Comment Date | Status | Date Closed | SSTL Comments
1 | Sprint-2 | WEB | pending approval | the screen is complete black it will not even show pending approval is zero | High | FU-Functional | 14/09/2023 | Ravishankar | Not part of Sprint-1. It will be implemented in Sprint-2 to display the pending tasks from Process Maker. 21-Sep>> Please check PSR backup slides for sprint items and Requirements/HLD for the detailed functionalities at the shared drive. | 21/9/23 | Resolved | 20/10/2023 | we need to know the details of sprint 1 and sprint 2 | please check no detailed report is given Senthil> Sprint items were given in PSR file and details are in the HLD doc. Please check below links HLD -> https://docs.google.com/document/d/1rLHAUQ19jMSuYFSLBzZiyQwQ59P-tZIz/edit?rtpof=true PSR->https://docs.google.com/presentation/d/19we10e9Yf0bdOwSS9YkSuyxaOCDfnkqQ/edit#slide=id.p7
2 | Sprint-2 | BOTH | Overall | the application on both web and mobile will never gets logged out it remains as it | High | IM-Improvement | 14/09/2023 | Ravishankar | Logout happens once Logout option is clicked. Auto Logout is not yet implemented. It will be implemented in Sprint-2 | 20/9/23 | Resolved | 20/10/2023
3 | Sprint-1 | MOBILE | near by sites | only technician can see this, superviser not able to see | High | FU-Functional | 14/09/2023 | Ravishankar | This is working fine. Both user can see near by sites. Will add some sites to your location after that please test again. 21-Sep> Added some nearby sites. Pls check now. | 21/9/23 | Resolved | 20/10/2023 | no site as been added till now. can we know the logic which we are working on
4 | Sprint-2 | MOBILE | if technician completets task | that task complition is not refelcting supervisors account , he should gets that notification | High | IM-Improvement | 14/09/2023 | Ravishankar | In sprint-1 we are allowing to update directly to database and approval feature is not yet implemented. It will be implemented in sprint-2 because PM approval is implemented in sprint2. | 21/9/23 | Resolved | 20/10/2023
5 | Sprint-1 | MOBILE | supervisor login page | nothing is working in supervisor account | High | FU-Functional | 14/09/2023 | Ravishankar | Data issue - This is working fine. Will add some sites to your location after that please test again. 21-Sep> Added some nearby sites. Pls check now. | 21/9/23 | Resolved | 20/10/2023
6 | Sprint-1 | MOBILE | adding new asset | this is not working | High | FU-Functional | 14/09/2023 | Ravishankar | Data issue - Please let us know if you are getting any error message. 21-Sep> It is working when we are doing this. Please retest. | 21/9/23 | Resolved | 20/10/2023 | adding new asset for eg new asset found in site cannot be added only if that asset is availble in FAR or SATS directory only with that serial no its added new asset cannot be added
7 | Sprint-1 | MOBILE | qr scanner | this function is not working | High | FU-Functional | 14/09/2023 | Ravishankar | Please let us know if you are getting any error message. | 20/9/23 | Closed | 21/09/2023
8 | Sprint-1 | MOBILE | battery bank | it is included in both active asset and passive asset as well | High | FU-Functional | 14/09/2023 | Ravishankar | Data issue - We have removed the data from active asset. Please retest | 20/9/23 | Closed | 21/09/2023
9 | Sprint-2 | MOBILE | child asset | when we add child asset we cannot reveiw it and also this notification we cannot see in supervisior details | High | FU-Functional | 14/09/2023 | Ravishankar | In sprint-1 we are allowing to update directly to database and approval feature is not yet implemented. It will be implemented in sprint-2 because PM approval is implemented in sprint2. | 20/9/23 | Resolved | 20/10/2023
10 | Sprint-2 | MOBILE | child asset details | incomplete information of child asset and we cannot see that when it is added and date, time and image. | High | FU-Functional | 14/09/2023 | Ravishankar | Data issue - Those could be dynamic attributes and not configured yet. Configuration management will be in sprint-2. | 21/9/23 | Resolved | 20/10/2023 | marked as irrlevant but when will be configured kindly provide us the details
11 | Sprint-2 | WEB | Operator site view | No image shown on desktop version | High | UI-Screen Cosmetics | 14/09/2023 | Ravishankar | Image view is not yet implemented in Web Protal. It will be implemented in Sprint2. | 21/9/23 | Resolved | 20/10/2023
12 | Sprint-1 | WEB | Asset History | No asset history for asset number: AT0011345AB | Low | MI-Minor | 14/09/2023 | Ravishankar | Data issue - History data not present for this assets. You can check serial no. DK12345239 | 21/9/23 | Resolved | 20/10/2023
13 | Sprint-1 | BOTH | No version | No IOS version available | Low | FU-Functional | 14/09/2023 | Harshajit Kalita | Communication started between Senthil & Ravishankar. Apple developer account is required for this. 27-Sep> Will generate IPA once android issues get resolved | 27/9/23 | On Hold | 20/10/2023 | As per UMT ios will be developed once the final version of Android is ready.
14 | Sprint-1 | WEB | Technician to Site Tagging Status | Some status dont match with color code eg: Showing red color code in Active status Asset (http://115.113.197.12:88/public/index.php/Technician_site_Worklist_view) | Medium | MI-Minor | 14/09/2023 | Harshajit Kalita | If there is no Asset Tag No then the color code for the asset will be red. No relation between asset status & tag colour. 21-Sep> No relation between tag color and asset status. If it is not tagged then the color will be red, if tagged then color will be green. | 21/9/23 | Closed | 20/10/2023 | Misunderstood the feature, clarified by UMT
15 | Sprint-1 | BOTH | Technician to Site Tagging Status | Naming convention is similar for type of asset (Active/ Passive) and status of asset (Active/inactive) | Low | IM-Improvement | 14/09/2023 | Harshajit Kalita | Asset Type will be either Active or Passive. Status of asset could be Active,Defective,Inactive,Missing,Redundant,Scrap 30-Oct> The Status value 'Active' will be rephrased as 'Used'. | 2023-11-02 | Resolved | 19/10/2023 | It was a suggestion and not necessary, but its confusing which was also raised by Crest in the Demo, Kindly have a look.
16 | Sprint-1 | WEB | Search Bar | Pressing Enter does does function, for search any field pressing enter does not work | Medium | MI-Minor | 14/09/2023 | Harshajit Kalita | The search is working on keypress, no need to press enter. 29-Sep> There is no enter button to search at Web App. Search works when user types text at the search box. | 29/09/2023 | Closed | 20/10/2023 | kindly provide us details why is it irrelevant, why the enter button will not work
17 | Sprint-1 | MOBILE | password | only once we can change the password after that we are unable to change it | Low | FU-Functional | 21/09/2023 | Ravishankar | 28-Sep> Change password working fine, please re-test. 31-Oct> Access control issue which is fixed and working fine. | 31/10/2023 | Resolved |  | facing the same issure still in new apk which is a new release in the sprint 3
18 | Sprint-1 | MOBILE | Task list | task list is not showing in the app | Low | FU-Functional | 21/09/2023 | Ravishankar | Please enter to this site "ST-WB-265", task list is there for this site | 21/9/2023 | Resolved | 20/10/2023 |  | Work flow issues
19 | Sprint-1 | MOBILE | asset audit button | this is not working | Low | FU-Functional | 21/09/2023 | Ravishankar | Login as Supervisor, enter into a site which having assests, then select audit option from hamburger menu | 21/9/2023 | Resolved | 20/10/2023 |  | Work flow issues
20 | Sprint-1 | MOBILE | Validate Search button | even after searching valid site id its saying data not found | Low | FU-Functional | 21/09/2023 | Ravishankar | Please provide the site ID which you are trying to search | 21/9/2023 | Closed | 20/10/2023
21 | Sprint-1 | MOBILE | Task list | task list is not showing in the app | Low | FU-Functional | 22/09/2023 | Ravishankar | This site "ST/HP/001", the data is not loading, working on this. | 22/09/2023 | Resolved | 20/10/2023
22 | Sprint-1 | BOTH | case senstive | all functions works only on capslock only no small will work | Medium | FU-Functional | 28/092023 | Ravishankar | Please mention which screen and where? It is working fine with both lower and upper case. Please check again. | 29/09/2023 | Resolved | 20/10/2023
23 | Sprint-2 | MOBILE | adding new asset | adding new asset is not possible if the asset not in FAR | High | FU-Functional | 28/092023 | Ravishankar | It is a change in existing functionality. Will be done in Sprint2. Will be available in upcoming release. 31-Oct> Implemented. | 31/10/2023 | Resolved |  | still improvement is required
24 | Sprint-2 | MOBILE | Adding child asset | adding new child asset is not possible if the asset not in FAR | High | FU-Functional | 28/092023 | Ravishankar | It is a change in existing functionality. Will be done in Sprint2. Will be available in upcoming release. 31-Oct> Implemented. | 31/10/2023 | Resolved |  | still it is not yet implimented
25 | Sprint-1 | BOTH | Task list and asset audit | presently tasklist is not showing in the app plus web, and it should be categorized according priority, and as well as site wise and date wise as well | High | FU-Functional | 28/09/2023 | Ravishankar | Task list (SRN, STN) is present at the Mobile App. Task list (approval request) for Supervisor will be present in screen at the WebApp and will be present in Sprint2. | 29/09/2023 | Closed | 20/10/2023
26 | Sprint-1 | MOBILE | Edit and modification | if we editing any asset only active or inactive status can be changed other things to be worked on it which will be mandatory points | High | FU-Functional | 28/092023 | Ravishankar | Status and Other fields are also editable. Working fine. 31-Oct> Attributes edit/modification is working fine. | 31/10/2023 | Resolved |  | edit and modification we need improvement in the attribute details
27 | Sprint-1 | MOBILE | asset audit button | once we scan during if we verify details, in asset details matching button only yes will work no button is not working | High | FU-Functional | 28/092023 | Ravishankar | This issue is fixed and will be available in upcoming release. | 29/09/2023 | Closed | 20/10/2023
28 | Sprint-1 | MOBILE | supervisor login page | if supervisor user clicks on any near by sites he himself get a notification by this will notified to supervisor but this is not working in technician user | High | FU-Functional | 28/092023 | Ravishankar | This is working fine for us, please note that that message appears when user clicks on the sites which are not in 'My Sites'. | 29/09/2023 | Closed | 21-10-2023
29 | Sprint-2 | BOTH | auto logout | auto logout after 30 min is implimented as per discussion it was implimentd in sprint 2 | Low | NF-Non-functional | 2023-10-11 | Ravishankar | Web Portal auto logout is set to 10 minutes. 11-Oct> Mobile APP side implementation work in progress 27-Oct> Resolved and released in 27Oct apk. 1-Nov> Resolved. 2-Nov> Not Resolved. Working on it. 3-Nov> Resolved. System will auto logout after 10 minutes of idle time. | 2023-11-03 | Resolved |  | facing same issue still kindly look into it
30 | Sprint-2 | WEB | adding new asset type | adding new asset type is possible but cannot save it | Medium | FU-Functional | 2023-11-09 | Ravishankar | This one is resolved. Kindly re-check. | 2023-11-10 | Resolved | 21-10-2023 | this is not resolved kindly check
31 | Sprint-2 | WEB | configaration management | need have details about date and the creator of the dataset(site) | Low | IM-Improvement | 2023-11-09 | Ravishankar | This is done. | 2023-11-02 | Resolved
32 | Sprint-2 | MOBILE | adding new asset type | adding a new asset is not possible and manufacture date is which we are not entering its not accepting | Medium | FU-Functional | 13/10/2023 | Ravishankar | Issue is not clear, please retest with latest apk. | 14/10/2023 | Resolved | 21-10-2023
33 | Sprint-2 | WEB | site asset view | date filter is required for approvals on the priority basis | Low | IM-Improvement | 13/10/2023 | Ravishankar | Scope of improvement, working on it. | 14/10/2023 | In-Progress
34 | Sprint-2 | WEB | proceess maker | accept and reject button is not working | Medium | FU-Functional | 13/10/2023 | Ravishankar | This is resolved. Please retest. | 14/10/2023 | Resolved | 21-10-2023
35 | Sprint-2 | BOTH | in site list assets are more in web but when we are checking in mobile it shows less | in site list assets are more in web but when we are checking in mobile it shows less Eg:site ID KA-088 bangalore | Medium | DI-Data Issue | 13/10/2023 | Ravishankar | Please recheck. | 14/10/2023 | Resolved | 21-10-2023
36 | Sprint-2 | WEB | proceess maker | when ticket is raised no mails are received for registered users | Medium | FU-Functional | 13/10/2023 | Ravishankar | Please recheck. | 14/10/2023 | Resolved
37 | Sprint-3 | MOBILE | Add Asset | we are not able to add asset even after giving the correct input | High | FU-Functional | 26/10/2023 | Ravishankar | Add Asset access right missing, hence access right given to technician to add new asset. | 26/10/2023 | Resolved
38 | Sprint-3 | MOBILE | Asset Tagging | once the technician tags an asset, thatt notification is not reflecting in webportal and also not receiving any mail regarding that | High | FU-Functional | 26/10/2023 | Ravishankar | This issue is fixed and released in sats_27oct23.apk | 27/10/2023 | Resolved |  | again recived new apk on 31st oct the apk is gets crashed instantly or in the condtion where it is not responsive kindly look on to it
39 | Sprint-3 | WEB | process maker | we can not reject any approval of asset in process maker | High | FU-Functional | 26/10/2023 | Ravishankar | This issue is fixed and released in sats_27oct23.apk | 27/10/2023 | Resolved
40 | Sprint-3 | MOBILE | auto logout | application is getting logged out many times even while using the application | High | FU-Functional | 26/10/2023 | Ravishankar | This issue is fixed and released in sats_27oct23.apk | 27/10/2023 | Resolved |  | received new apk on 31st oct we are still facing certain crash of apk kinldy provide us proper apk we can do the complete testing on it
41 | Sprint-3 | MOBILE | perfomance issue | The apk is lagging so much and consuming a bettery so much | High | FU-Functional | 26/10/2023 | Ravishankar | Working on it. | 27/10/2023 | In-Progress
42 | Sprint-3 | MOBILE | Functional | As a technician, there should be restriction for then, that when they visit to site , then only they would be able to view the asset and be able to tag, untag the asset | Medium | IM-Improvement | 30/10/2023 | Rajnee | Need further discussion on this enhancement. 2-Nov> On hold now as per discussion. | 2023-11-02 | On Hold
43 | Sprint-3 | WEB | Funtional | User Management board should be removed from the dashboardm if we login to user mgmt, or should be highlighted to differnt color,as when we click it , it goes to some failure msg. | Low | IM-Improvement | 30/10/2023 | Rajnee | Resolved | 30/10/2023 | Closed
44 | Sprint-3 | MOBILE | My task | while clicking on My task it is not redirecting to my as mentioned in test cases | Low | FU-Functional | 30/10/2023 | Ravishankar | My Task is now changed to Task List and working fine. | 30/10/2023 | Resolved
45 | Sprint-3 | MOBILE | change password | technician and supervisor can not change password the message displays this user dont have an access to change the password | Medium | FU-Functional | 30/10/2023 | Ravishankar | Access rights granted to the respective roles. | 30/10/2023 | Resolved
46 | Sprint-3 | MOBILE | both technician and supervisor can search the site | this access should be restricted to supervisor | Medium | IM-Improvement | 30/10/2023 | Ravishankar | This can be restricted with respective Access rights which is configurable. | 30/10/2023 | Resolved
47 | Sprint-3 | MOBILE | Validate the Email to the supervisor | if technician opens any site pop will appear saying unassigned site but this notfication is not sent to supervisor. | Medium | FU-Functional | 30/10/2023 | Ravishankar | Resolved | 30/10/2023 | Resolved |  | still no notification is to supervisor on this
48 | Sprint-3 | WEB | New User not recieving mail | When a new user is added in user managment, doesnt recieve any mail notification | High | FU-Functional | 30/10/2023 | Rajnee | Resolved | 31/10/2023 | Resolved |  | not resolved kindly recheck it
49 | Sprint-3 | MOBILE | edit of asset | in the edit option we need improvise the attribute details , now it shows only asset name, status and make we need to add some more details in it | Medium | IM-Improvement | 30/10/2023 | Ravishankar | Please configure more asset attribute and then edit. | 31/10/2023 | Resolved |  | need an explaination
50 | Sprint-3 | MOBILE | adding child asset | when we are adding child asset we dont have option of tagging it and taking a picture of it | High | FU-Functional | 30/10/2023 | Ravishankar | Working on it. | 30/10/2023 | In-Progress
51 | Sprint-3 | MOBILE | adding child asset | adding child asset is not notified to supervisor | Medium | FU-Functional | 30/10/2023 | Ravishankar | This is working fine. | 31/10/2023 | Resolved
52 | Sprint-3 | MOBILE | auto logout | even still while using the application gets auto logout | Low | FU-Functional | 30/10/2023 | Ravishankar | Duplicate (#29) | 31/10/2023 | Closed
53 | Sprint-3 | MOBILE | multiple user | in same account simultaneously multiple users can login and can use | Low | FU-Functional | 30/10/2023 | Ravishankar | As per Ravi, multiple active session should not be allowed for same user. | 31/10/2023 | Open
54 | Sprint-3 | MOBILE | asset addition | even if we are adding invalid details during asset addition its gets added | Low | FU-Functional | 31/10/2023 | Ravishankar | It is a free low field. | 31/10/2023 | Closed | 2023-02-11 | there must be certain fixed attributes but it accepts everything
55 | Sprint-3 | MOBILE | asset addition | during asset addition we dont have option to tag and take a picture of new asset | High | FU-Functional | 31/10/2023 | Ravishankar | Working on it. | 31/10/2023 | In-Progress
56 | Sprint-3 | MOBILE | asset addition | while adding new asset if that asset as a child asset we dont have an option to add any child asset for that new asset | Medium | IM-Improvement | 31/10/2023 | Ravishankar | User will add parent asset first and then go for adding childs. | 31/10/2023 | Open |  | so need to do the process twice we can not do at a time
57 | Sprint-3 | MOBILE | QR code | scanned same QR code for many assets it accepted it and it did not show any error on. QR code should be always unique for every single asset | High | FU-Functional | 31/10/2023 | Ravishankar | Resolved. | 2023-01-11 | Resolved |  | not working fine we tag same QR code for many assets
58 | Sprint-3 | MOBILE | STN process | we have to match the asset details which are matching ,but if those details are not matching we dont any option for miss match | High | FU-Functional | 31/10/2023 | Ravishankar | Working on it. STN Details would be editable. | 2023-11-01 | In-Progress
59 | Sprint-3 | BOTH | SRN | while rejecting srn no notification sent to supervisor and it still remains in task list unless we accept it | High | FU-Functional | 31/10/2023 | Ravishankar | Working on it. | 2023-11-01 | In-Progress
60 | Sprint-3 | MOBILE | STN process | technician can not see any details about the asset in STN process he as site address and remarks need more information to identify on it | Low | IM-Improvement | 31/10/2023 | Ravishankar | User can see the details after opening the STN. | 2023-01-11 | Closed | 2023-02-11
61 | Sprint-3 | MOBILE | STN and SRN | while asset tagging technician can not click on ok button to submit its not working and in both STN and SRN submit button is not working | high | FU-Functional | 31/10/2023 | Ravishankar | Unable to replicate this issue. | 2023-01-11 | Resolved |  | when unable to replicate the issue how is it resolved??
62 | Sprint-3 | BOTH | login | during login if we are entering the first letter in caps we will be not able to login it throws an error | Medium | FU-Functional | 31/10/2023 | Ravishankar | User id is made case insensitive. | 2023-11-03 | Resolved
63 | Sprint-3 | MOBILE | asset audit | once asset audit is done and colour code turns green, and if reclick on asset audit again it shows red in colour we can redo the asset audit. unless ticket raised by the user is cleared how can we redo the audit for the same asset | Medium | IM-Improvement | 31/10/2023 | Ravishankar | Need further discussion on this enhancement. 2-Nov> Closed as per discussion. | 2023-11-01 | Closed | 2023-11-02
64 | Sprint-3 | WEB | user management | the check box which is provided when user is created, only supervisor check box is availble but a check box for all the roles should be there | medium | IM-Improvement | 31/10/2023 | Rajnee | Check box is not required for other roles than supervisor. This check box is given so that system can identify the supervisor user during Technician-Supervisor mapping.. | 2023-01-11 | Resolved
65 | Sprint-3 | WEB |  | who creates admin id | question | FU-Functional | 31/10/2023 | Rajnee | This is the default user of the system and will be used to create first user in the system. | 2023-01-11 | Resolved
66 | Sprint-3 | WEB | login details | in the web portal the user dont have any option to reset the password | Medium | IM-Improvement | 31/10/2023 | Ravishankar | User will login into user mangement and do change password. | 2023-01-11 | Resolved
67 | Sprint-3 | MOBILE | asset addition | while adding new asset if we are adding the availble asset with same serial it adds the asset and say the asset is not found | High | FU-Functional | 2023-11-02 | Ravishankar | This issue is resolved. | 2023-11-03 | Resolved
68 | Sprint-3 | WEB | user Management | whenever new user is created, welcome mail recieved by the user is incomplete | Medium | MI-Minor | 2023-03-11 | Rajnee | Please suggest the mail text. | 2023-11-03 | In-Progress |  | Welcome mail, along with what to donwload or where to downlaod even credentials are needed
69 | Sprint-3 | MOBILE | Add Asset | while addition an asset, for diameter are able to enter alphanumeric value | Low | MI-Minor | 2023-03-11 | Rajnee |  |  | In-Progress
Resolution Time (UMT)
|  |  | High | 24 hours
|  |  | Medium | 36 hours
|  |  | Low | 48 hours
Retesting time (SSTL)
|  |  | High | 24 hours
|  |  | Medium | 36 hours
|  |  | Low | 48 hours

## Screenshot
Point No 43
point 69