## Sheet1
Sl No | Defect ID |  | Problem Description | Solution | Status | Suppport Required | RESPONSE
1 | 343 |  | Invoice Pendency Report Required | As per the specs, the invoice pendency report will contain the following: Input criteria : date range. Validation- End Date cannot be less than Start Date and End Date cannot be greater than current date. While fetching, maximum one year of the data can be fetched in one go. Processing logic - All sites along with the missing invoice periods (for any specific landlords) for which there are no invoice records available in LMS between the date range provided.Output- Site Id, Site Name, Circle, Type of Lease Premises Landlord Id, Landlord Name, Vendor Code, Invoice Type (Rental/EB), Invoice Frequency, Missing Invoice Period in tabular format. There can be multiple records for one Site Id if invoices for multiple periods are not processed. | W.I.P | Clarification sought on solution concurrence on 2nd Jan '24 | Please share the mock report for validation and sign-off
2 | 362 | Common | STIPL-AP-616 - when site was integrated from TT to LMS - site city attribute Address values are not correct - means address value is reflecting 'Kurnool' instead of 'GGN' and city value is reflecting blank insted of 'Kurnool'. Solution Type, City and Project Status Value are also blank. Solution Type is not Correct |  | W.i.P
3 | 431 | Suraj Jain | Solution Type is not populated from Tenantes to Attribute screen | This is fixed, and will reflect to new data imports from TT. The solution type mentioned in TT data will reflect in tenant screen and the same details will also reflect under site attribute. | Resolved
4 | 440 | Makrand Jain | In agreement Screen and Ticket Attribute in Tasks Attribute - Assigned To & Assigned Date are not capturing | The viewing is only applicable for Tickets with their status Open. Both fields "Assigned to" and "Assigned Date" will reflect relevant data of the ongoing task. The same could be viewed from Site-> Tockets-> View any task with Open status. | Resolved | Clarification Sought on Solution concurrence | The Assigned to and date fields are required to track the person responsible and when was it assigned, Open tickets only will have Assigned to and Assigned date. Closed tickets do not need this information
5 | 444 | Suraj Jain | In agreement Screen - we created 8 agreements ID but tickets are available only for single agreement ID 347. Point observed in Site Guj/030 agreement ID 384 | Workflow tickets will be created for both Main and Addendum agreements only (the addendum agreement is added to workflow as per requirement capture during Dec 22 '2023 | Resolved
6 | 450 |  | In Agreement Screen - The changes what we have done those are not capturing in event screen. Point observed in Site KTK-281 agreement ID 391 (Screen shots are attached) |  | W.I.P
7 | 455 |  | In case of First Agreement is existing and pending for approval / activation - another agreement should not be processed. Now System is showing error but creating the agreement | This was a bug where the approval was getting triggered after | Resolved
8 | 458 |  | If we are editing the exist active agreement and just save the agreement without any changes - again it is going for approval process | Saving any agreement without making any changes will not initiate workflow. | Resolved
9 | 470 |  | In invoice screen - when we are entering the TDS and GL code input, same time and clicking on SAVE TDS then GL Code input is vanishing | A single save, approve and diapprove button for batch selection of invoices allowing modification of TDS and GL Code. The GL code input will only get validated using GL Code masters. Please note that the expected behaviour of the Invoice management screen will be to prevent any further edits to invoices which are already approved by FInance, these invoice details will be greyed out and any edition will be prevented by system. | Resolved
10 | 472 |  | Particular Service - Particular Site - Particular Vendor - Particular Period Overlapping period invoices should not be accepted by system | We have shared a test case with SSTL, where we have simulated the use case. The system will prevent saving of invoices with overlapping date range for same site and landlord with same invoice type. | Resolved | Clarification sought on solution concurrence 30 Dec 23 (Test case shared) | To be tested for all scenarios by SSTL before sign-off. Will be done on the UAT environ, before releasing to UMT
11 | 443 | Suraj Jain | In agreement Screen - Main agreement can not be created multiple times untill unless old existing main agreement will not be deactivated. Point observed in Site Guj/030 agreement ID 384 | Main agreement can be created more than once only under circumstaces the agreement tenures are mutually exclusive (after expiry of current agreement, the next available main agreement by its dates becomes affective. This was explained to client during our meeting at Delhi | Resolved | Clarification sought on Solution concurrence | To be tested for all scenarios by SSTL before sign-off. Will be done on the UAT environ, before releasing to UMT
12 | 323 |  | How we can get the information that how many LL's SAP code has been created and how much are pending | As per our discussions with the client during Dec 22 2023, we have deviced a script which will list all Lanlord ID's that do not contain Sap vendor code and will be mailed to intended receipent twice daily | Resolved | Clarification sought on 27th Dec '23 w.r.t frequency of the email and receipent mail ID | Twice daily. Create a workgroup with Makrand and Suraj E-mail ID. Should have provision to add/ delete reciepents,
13 | 370 | Common | TDS should be updated in decimal value also and should not be udpated more then two digits | Validation to TDS input will be allowed till <=20.00%, decimal is allowed till two digits | Testing Pending
14 | 422 |  | Select All - Option required while approving / rejecting invoices | Multiple selections is now allowed for approving and rejection of agreements | Resolved
15 | 423 | Amer Shrivastav | In approved Agreement - If we are adding an addendum agreement - it got activavted and linking with site without any approval (For exp: site id AP-231 - Agreement ID 387) | Similar workflow process like main agreements will be added for addendum agreements. | Resolved
16 | 424 | Amer Shrivastav | In approved Agreement - If we are removing existing main / addendum agreement - it is de-activavting from site without any approval | Requirement is not as per scope, however, during 23rd Dec '23, we did discuss a solution to restrict the access to deactivate or remove main or addendum agreements using access control | Testing Pending | Clarification sought (26-12-23) w.r.t Consolidated list of users with rights to modify and deactivate agreements. | Twice daily. Create a workgroup with Makrand and Suraj E-mail ID. Should have provision to add/ delete reciepents,
17 | 364 | Common | City, Project Status, Solution Type should not be editable field because these filelds are capturing from TT | City, Project Status and Solution Type are made non Editable fields | Resolved
18 | 368 | Common | Electric Meters - Once EB meter will be removed - it should be reflected deactivate with deactivate date instead of meter got completely removed from system | The use of an EB meter entry in LMS is only for mapping the meter number and capturing corresponding readings from galaxy . Here in our discussion during 22nd Dec '23 , this was discussed that the EB meter deletion will be restricted using an access control to few users only | Testing Pending | Clarification sought (26-12-23) | Twice daily. Create a workgroup with Makrand and Suraj E-mail ID. Should have provision to add/ delete reciepents,
19 | 369 | Common | Electric Meters - Once EB meter will be added / removed - it should be active/deactivate with designed approval, now system is allowing to active or remove the meter without any approval | Entry of any wrong or additional meter number in the system will not have any impact because if the meter serial number doesn't match with Galaxy data , it will not capture any readings. In our meeting with Crest during Dec 22, '23, it was discussed that this particular requirement will be addressed using an user access control workgroup settings | Testing Pending | Clarification sought (26-12-23) | Twice daily. Create a workgroup with Makrand and Suraj E-mail ID. Should have provision to add/ delete reciepents,